## 1. Test Scenario
Project Name | OrangeHRM website testing
Reference Document | N/A |  | P1= Highest Priority
Created by | S. M. ASHIL REZA |  | P2= Medium Priority
Creation Date | 2022-03-11 |  | P3= Low Priority
Date of review | 2022-04-11
Review By | AKHTER HAMID SAYMON
Test scenario ID | Test Scenario Description | Priority | Number of Test Cases
TS_01 | Check the horizontal navigation Bar/ menu functionality. | P1 | 8
TS_02 | Check the footer navigation menu functionality. | P2 | 3
TS_03 | Check the Sign up page functionality. | P1 | 6
TS_04 | Check the booking page functionality. | P1 | 4
TS_05 | Check the contact sale page functionality. | P1 | 4

## 2. Test Case
Document Name | Test Case
Created By | s. m. ashil reza
step 1: open the browser (microsoft edge)
step 2: go to URL: https://www.orangehrm.com/
Test Case ID | Test scenario ID | Test Case Title | Test Steps | Test Data | Expected Result | Actual Result | Status
TC_01 | TS_01 | Check that the user can access the "Book A free demo" Page by clicking the Book A free Demo button. | Click on the "book a free damo" button | Null | Users will be able to visit the book a free damo page of this website. | As Expected | Passed
TC_02 | TS_01 | Check that the user can access the "Contact sale"page by clicking the contact sale button. | Click on the "contact sale" button | Null | Users will be able to visit the contact sale page of this website. | As Expected | Passed
TC_03 | TS_01 | Check that the user can got o home page by clicking on the Logo | Click on the Logo | Null | Users will be able to go the home page of this website. | As Expected | Passed
TC_04 | TS_01 | check that the user can access the "platform" option by taking the curser on the Platform option | point the course on "platform" option | Null | Users will be able to open te Platform topup option | As Expected | Passed
TC_05 | TS_01 | check thatthe user can access the "Why OrangeHRM" option by taking the curser on the Why orangeHRM option | point the course on "Why OrangeHRM" option | Null | Users will be able to open te Why OrangeHRM topup option | As Expected | Passed
TC_06 | TS_01 | check that the user can access the "Resource" option by taking the curser on the resource option | point the course on "resource" option | Null | Users will be able to open te Resouce topup option | As Expected | Passed
TC_07 | TS_01 | cehck tha the user can access the "Company" option by taking the curser on the company option | point the course on "company" option | Null | Users will be able to open te company topup option | As Expected | Passed
TC_08 | TS_01 | Check that the user can access the "Try is for free" Page by clicking the try it for free button. | Click on the "Try it for free" icon button | Email: qce76331@nezid.com | Users will be able to visit sign up page of this website. | As Expected | Passed
TC_09 | TS_02 | Check that the user can visit the facebook page of the acquireangel by clicking the facebook button. | Click on the "facebook" icon button | Null | Users will be able to visit facebook page of this website. | As Expected | Passed
TC_10 | TS_02 | Check that the user can visit the linkedin page of the acquireangel by clicking the linkedin button. | Click on the "linendin" icon button | Null | Users will be able to visit linkedin page of this website. | As Expected | Passed
TC_11 | TS_02 | Check that the user can visit the youtube page of the acquireangel by clicking the youtube button. | Click on the "youtube" icon button | Null | Users will be able to visit youtube page of this website. | As Expected | Passed
TC_12 | TS_03 | Check that the signup page contain resgistartion option with submit button. | 1. enter a valid email , 2.Click on the "try it for free" button | Email: qce76331@nezid.com | Users will be able to visit sign up page of this website. | As Expected | Passed
TC_13 | TS_03 | Check that the signup page contain full name, email address, adress, present address, country, mobile number with country code in registration option | enter the signup option using an email and click the try it for free button | Email: qce76331@nezid.com | the page contain favoured name, full name, email and phone number and cournty | not As Expected | Failed
TC_14 | TS_03 | Check that the user can register with invalid information on signup page and click the submit button for registration | 1. enter valid email 2. Click on the "try it for free" button with valid email | valid email: qce76331@nexid.com Name: S. M. ASHIL REZA email: ashilrezasporsho@gmail.com country: england mobile number: 01795080690 | Users will not be able to registarion on signup page with invalid information | As Expected | Passed
TC_15 | TS_03 | Check that the user can register with valid information on signup page and click the submit button for registration | 1. enter valid email 2. Click on the "try it for free" button with valid email | email: qce76331@nexid.com favored name: ashilreza Name:REZA country: Bangladesh mobile number: 01795080690 | Users will be able to visit youtube page of this website. | As Expected | Passed
TC_16 | TS_03 | Check that after submiting all valid information and submit that then open signin page | 1. enter valid information 2.Click on the "submit" icon button | Null | stay in the same sign up page | not As Expected | failed
TC_17 | TS_03 | Check that after submiting all valid information and submit that then open home page | 1. enter valid information 2.Click on the "submit" icon button | Null | stay in the same sign up page | not As Expected | failed
TC_18 | TS_04 | Check that after submiting invalid information and submit and shows error for the invalid information | 1. click on Book a Free Demo buttion 2. enter invalid information 3.Click on the "submit" icon button | email: qce76331@nexid.com favored name: sporsho Name:Sporsho mobile number: 01795080690 | showing the error of the invalid inforrmation | As Expected | Passed
TC_19 | TS_04 | Check that after submiting valid information and submit and booked with that valid information | 1. click on Book a Free Demo buttion 2. enter invalid information 3.Click on the "submit" icon button | email: qce76331@nexid.com favored name: ashilreza Name:REZA mobile number: 01795080690 | Users will be able to booked | As Expected | Passed
TC_20 | TS_04 | Check that after submiting valid information, shows a topup for success ful registarion | 1. click on Book a Free Demo buttion 2. enter invalid information 3.Click on the "submit" icon button | Null | Users will not be able to see any topup for success done notification | not As Expected | failed
TC_21 | TS_04 | Check that after submiting valid information, anotherpage for showing booking details | 1. click on Book a Free Demo buttion 2. enter invalid information 3.Click on the "submit" icon button | Null | Users will not be able to booking details page of this website. | not As Expected | failed
TC_22 | TS_05 | Check that after submiting invalid information and submit and shows error for the invalid information | 1. click on contact sale buttion 2. enter invalid information 3.Click on the "submit" icon button | email: qce76331@nexid.com favored name: sporsho Name:Sporsho mobile number: 01795080690 | showing the error of the invalid inforrmation | As Expected | Passed
TC_23 | TS_05 | Check that after submiting valid information and submit and booked with that valid information | 1. click on contace sale buttion 2. enter invalid information 3.Click on the "submit" icon button | email: qce76331@nexid.com favored name: ashilreza Name:REZA mobile number: 01795080690 | Users will be able to submit | As Expected | Passed
TC_24 | TS_05 | Check that after submiting valid information, shows a topup for successfully registarion | 1. click on contact sale buttion 2. enter invalid information 3.Click on the "submit" icon button | Null | Users will not be able to see any topup for success done notification | not As Expected | failed
TC_25 | TS_05 | Check that after submiting valid information, anotherpage for showing saling details | 1. click on contact sale buttion 2. enter invalid information 3.Click on the "submit" icon button | Null | Users will not be able to saling details page of this website. | not As Expected | failed

## 3. Bug Report
| Document Name |  | Bug Report |  |  | step 1: open the browser (microsoft edge)
| Created By |  | S. M. ASHIL REZA |  |  | step 2: go to URL: https://www.orangehrm.com/
Bug Id | Test Case Id | test scenario Id | Bug Title | Location | Bug Description | Reproducing Steps | Enviroment Details | Expected Result | Actual Result | Attachments | Priority | Assignee
B_AA_01 | Tc_13 | TS_03 | The signup page does not contain enough option for registration | sign up page | it contains some information for registration but lakings do some important information such as address, permanet address, birthdate, blood group etc | 3. Go to the HomePage horizontal navigation Bar/ menu section 4. Click on try it for free Button | Browser: microsoft edge OS: Windows 10 pro | the page contain favoured name, full name, email and phone number and cournty | Not as expected, detailed in the bug description | Before bug: https://ibb.co/H4Ltx8Q After Bug: https://ibb.co/7QcTZhc | P1 | TBA
B_AA_02 | Tc_16 | TS_03 | after signup, doesn't open new page for sign in | sign up page | when signup with valid information and click the submit buttion, the page stay in the same page | 3. Go to the HomePage horizontal navigation Bar/ menu section 4. Click on try it for free Button | Browser: microsoft edge OS: Windows 10 pro | after givern all valid information and click submit button the page show take another page for sign in or go to home page for log in | Not as expected, detailed in the bug description | Before bug: https://ibb.co/H4Ltx8Q After Bug: https://ibb.co/7QcTZhc | P1 | TBA
B_AA_03 | Tc_17 | TS_03 | after signup, doesn't open new page for sign in | sign up page | when signup with valid information and click the submit buttion, the page stay in the same page | 3. Go to the HomePage horizontal navigation Bar/ menu section 4. Click on try it for free Button | Browser: microsoft edge OS: Windows 10 pro | after givern all valid information and click submit button the page show take another page or go to home page for login or signin | Not as expected, detailed in the bug description | Before bug: https://ibb.co/H4Ltx8Q After Bug: https://ibb.co/7QcTZhc | P1 | TBA
B_AA_04 | Tc_20 | TS_04 | missing notification for successfully booked | book a free demo page | after registration, there are not showing any topup notification status | 3. Go to the HomePage horizontal navigation Bar/ menu section 4. Click on Book a free demo Button | Browser: microsoft edge OS: Windows 10 pro | it should be show the user as topup notification status for assure them the successfully registration | Not as expected, detailed in the bug description | Before bug: https://ibb.co/H4Ltx8Q After Bug: https://ibb.co/7QcTZhc | P1 | TBA
B_AA_05 | Tc_21 | TS_04 | missing booking details information | book a free demo page | after registration, there are not showing any details about booking | 3. Go to the HomePage horizontal navigation Bar/ menu section 4. Click on Book a free demo Button | Browser: microsoft edge OS: Windows 10 pro | it should be show the user booking details after book on a new page or same page | Not as expected, detailed in the bug description | Before bug: https://ibb.co/H4Ltx8Q After Bug: https://ibb.co/7QcTZhc | P1 | TBA
B_AA_06 | Tc_22 | TS_04 | missing notification for successfully contact sale registration | contact sale page | after registration, there are not showing any topup notification status | 3. Go to the HomePage horizontal navigation Bar/ menu section 4. Click on contact sale Button | Browser: microsoft edge OS: Windows 10 pro | it should be show the user as topup notification status for assure them the successfully registration | Not as expected, detailed in the bug description | Before bug: https://ibb.co/H4Ltx8Q After Bug: https://ibb.co/7QcTZhc | P1 | TBA
B_AA_07 | Tc_23 | TS_04 | missing contact sale details information | contact sale page | after registration, there are not showing any details about contact sale | 3. Go to the HomePage horizontal navigation Bar/ menu section 4. Click on contact sale Button | Browser: microsoft edge OS: Windows 10 pro | it should be show the user contact details of saling on a new page or same page | Not as expected, detailed in the bug description | Before bug: https://ibb.co/H4Ltx8Q After Bug: https://ibb.co/7QcTZhc | P1 | TBA